## Slide 1: Transition Project Oratory RC primary
Rationale
The project aim was to improve the Year 6 to Year 7 transition process for parents and pupils with a particular focus on send pupils.

## Slide 2: Project Implementation plan of action using the OAG for guidance and resources
Project Planning and Stakeholders
  The project was planned from May to October 2025 with a focus on supporting send pupils and parents with transition from Year 6 and year 7.
Data Collection
  Parent and pupil questionnaires informed the content of the transition support programme.
Engagement with Secondary Schools
  feeder secondary schools were contacted to ensure smooth transitions for SEND pupils, including additional visits, and to share key information.
PUPIL transition information sessions
  Whole class sessions helped pupils prepare for transition day and helped them share ideas for questions they might want to ask on the day. Videos helped children understand how they might feel and what they could do to engage with new people.
  Evaluations, and Final Reporting
  Pupils and parents gave feedback on the process which led to adaptions in the process for the following year.
  Moving forward
  Transition offer to include earlier information sharing, support with applying for secondary and support for visiting secondary schools.

## Slide 3: Additional tailored support
Additional visits
  Early communication with Receiving schools to plan additional visits for children with send
SEND reviews
  Receiving secondary schools invited to attend summer term reviews for children with send.
Finding the right school
  List of local secondary schools, resource bases and specialist schools shared with SEND parents where appropriate to need.
Individual pupil sessions with sendco
  Individual discussion with sendco after whole class transition sessions to support individual needs of SEND pupils.
  One-page profiles
  Share SEND pupils’ one-page profiles with receiving schools.
  Transfer of information
  Share individual SEND records with receiving schools in a timely manner.

## Slide 4: Insights from Pupil Questionnaire
Emotional Responses and Expectations
  Pupils expressed excitement about new opportunities but also anxiety about adapting to secondary school life.
Transition Support Activities
  Whole class sessions, staff visits, and interactive sessions helped pupils feel more prepared and less anxious about the transition.
SEND Pupil Inclusion
  Additional tailored support, sharing of individual needs information and visits to secondary schools, ensured SEND pupils' needs were addressed effectively.
Importance of Feedback
  Pupil and feedback was crucial in refining the transition offer to meet pupils’ actual experiences and needs.

## Slide 5: Pupil Questionnaire Quotes
SEND pupil concerns
Is there going to be a bigger classroom?
Will the teachers help me if the work is too hard and I don’t get it?
How will I get to each class on time?
If I am in a set and the work is too easy, can I move up?
What is it like in my new school?
Is it hard?
Are there bullies?
What time does it close?
what pupil’s thought might help them:
Books
Stationery
The teachers helping me in every lesson
People helping me and showing me where to go
A map of the school
Meet some teachers and Going around the school to see where everything is before I start there
Buses/transport
A laptop
Friends and teachers
To be able to speak in front of my class
Making friends
Other comments from pupils:
I’ve been to the school because my brothers go there
I went to my school yesterday
Are there going to be trips?
I want to make new friends
My mum is going to take me to see my new school in the summer
I’m happy with the school I’ve chosen
One child became frustrated when talking about his new school and said that he didn’t want to talk about it.

## Slide 6: Pupils feedback before and after transition
Feedback Category | Before Transition | After Transition
Nervous/Worried | 38% | 0%
Partly Confident | 25% | 50%
Very Confident & Happy | 0% | 50%
Unsure About Meeting Teachers | 24% | 0%
Unaware of Preparation Activities | 62% | 0%
Aware of Preparation Activities | 0% | 100%
Emotional Reassurance
  Pupils emphasise staying positive and confident during the transition to secondary school.
Positive Reflection
  Pupils express overall satisfaction with the transition process and school experience.
Pupils’ advice for current Year 6 pupils
“Be happy and smile because be happy to go to a new place even if not confident. It’s ok to not be confident. Follow people around and you’ll be ok. On another day, you won’t need to follow.”
“Always do your homework.” “I go to homework club.” “I’ve made new friends.”
“The uniform is good.”
“School is good sometimes.” “I like staying in the same class for a lot of lessons.”

## Slide 7: Feedback from Parent Questionnaire
Positive Parent Reception
  Parents appreciated proactive communication and diverse support such as information coffee mornings, signposting to support.
Inclusive Engagement
  Parental involvement in planning and feedback helped address concerns about emotional readiness and school information.
SEND Support Impact
  SEND support groups and meetings with staff from receiving feeder schools eased anxieties and ensured smoother transitions for pupils.
Suggestions for Improvement
  Parents recommended earlier engagement and more detailed secondary school routine information for future planning.

## Slide 8: Parent Questionnaire quotes
Parents concerns/worries
How will he cope with the multitude of changes?
That he will find it too overwhelming and not want to go as it will be a lot more work.
Bullies
Not sure
Parents questions
Will he have an opportunity to visit the school beforehand?
Will he be able to get transport to get to school?
Will he have the right support in place so if he struggles, he’ll be ok?

## Slide 9: Feedback from Parents
Positive Transition Feedback​
Parents expressed appreciation for detailed information and opportunities to meet teachers before transition.​
Successful Transition Outcomes​
Quotes like 'Settled in well'; 'Lots of information during the transition'; 'Opportunities to visit the school and meet the teachers who would be involved in Y7 as a point of reference really helped with transition for my son', highlight the effectiveness of the transition programme in easing pupil adjustment.​
Need for Improved Communication​
Parents suggested more communication on homework and school events for better academic support.​
Digital Communication Integration​
Use of social media platforms recommended to enhance engagement and information sharing with parents.
​ | Before Transition​ | After Transition​
Support for Parents​ | 57% did not expect support​ | 75% felt supported and confident, 25% partly confident​
Information and Involvement​ | 43% felt uninformed and uninvolved​ | 75% felt fully involved and informed, 25% wanted more involvement​
Confidence in Child's Transition​ | 71% not confident​ | 50% very confident, 50% quite confident​
Perceived Child Confidence​ | Not measured​ | 100% felt child was confident or quite confident​

## Slide 10: PLANNING SUGGESTIONS FOR PRIMARY
Early support
  Beginning of September Invite year 5/6 parents to a transition meeting to discuss visiting secondary schools.
  Provide a list of local schools and the dates for open days.
  Visit special schools/resource bases with parents if requested/appropriate to needs.
Secondary transfer form completion
  Mid-September invite year 6 parents in to offer support with completing secondary transfer forms online.
  Provide send parents with a list of Resource bases/special schools if appropriate to need.
Send support
  Summer term Send parent transition support meeting for year 4/5 parents to discuss concerns and what questions they might ask when visiting secondary schools.
  Invite new schools to summer term reviews and or to meet the child and parents.
  arrange additional visits where appropriate.
Secondary transition days
  Spring term year 6 Parents meeting to share transition resources and sign posting to useful websites.
  Summer term Whole class pupil sessions around what to expect on transition day and develop questions to ask – use BBC bitesize and young minds online resources.
  Follow up whole class session to discuss transition day experiences and build confidence.
Sharing send information
  End Summer term share one-page profiles and send information with receiving schools.
  Create/suggest creation of transition books where appropriate to support send pupils.

## Slide 11: Suggested resources/links used during this project to support transition from primary to secondary school were taken from the oag for transition
  https://www.bbc.co.uk/bitesize/articles/zkb747h
  https://www.annafreud.org/resources/schools-and-colleges/moving-up-the-transition-to-secondary-school/
  https://www.youngminds.org.uk/professional/resources/supporting-school-transitions/
  https://www.birmingham.gov.uk/info/20119/school_admissions
  https://www.bbc.co.uk/bitesize/groups/c5vpkq1l934t