## Slide 1: Transition from Nursery to Reception
Providing children with the appropriate support during the transition leads to children settling well into the next step in their learning journey.

## Slide 2: What we set out to do:
Our aim for this project was to enable successful transition for our children with lower self esteem and confidence, speech and language needs and who may struggle to settle into a new setting (school).
We wanted to ensure parent/ carers were well prepared and knew how to ensure their child was getting ready for school.
We also wanted to develop our links further with the receiving schools to support the transition of these children.

## Slide 3: What We Planned:
Identified two main settings to work with. One with established good links with the DLP and one where we wanted to develop it further. Contact was made with both schools who agreed to take part in the project.
Shared Transition OAG with both settings when planning transition support. Project allowed for further support using the Transition OAG if needed.
DLP transition event – and feedback forms from professionals
Additional visits in the receiving settings
Opportunities for new class teachers to observe in current settings
Parent/ carer workshops to support transition and feedback completed
Ready Steady Reception programmes to be run
To have additional meetings with Sencos and writing SSPPs for those who require them
Sharing of one page profiles and additional needs with receiving settings.
To have additional 1-1 meetings with parents/ carers to support the transition of their child

## Slide 4: What we did as a DLP and feedback
As part of our DLP work we facilitated a transition event inviting local schools and providers to come together to “hand over” the children to their receiving school. We ran one in Northfield district and one in Edgbaston district. These events were well attended and lots of new relationships were developed between EY settings and primary schools. There were also professionals who attended; Startwell, occupational therapists and Edgbaston and Northfield family hubs.
We also introduced a transition song and book in the Northfield district. This was well received by the settings and they gave really positive feedback. The only challenge for this event was, some settings were booked on but did not attend on the day; due to low staff numbers etc.
Some of the feedback included; “useful event,” “Thanks for organising it, all were approachable and helpful.” “I would definitely attend again,” “great morning, lots of information shared.”
The settings commented on what went well, “having the time to discuss the child and paint a picture of who would be attending the school,” “it was such a brilliant concept and has saved me time ringing or visiting pre school settings.”

## Slide 5: What we did for parents and feedback
We planned additional 1-1 meetings with parents to support the transition of their child where necessary.
We ran parent a workshop on transition and these were very well attended.
We discussed how children transitioned to school, used Ready, Steady Reception to discuss the skills they need to develop before attending school. We also discussed expectations of school and the expectations of parents. There were uniforms on display, lunch boxes and examples of social stories for reference, general information about the school day and curriculum.
The parental feedback was very positive. Parents reported, “ The workshop brought up things the I hadn’t even thought about,” “ Helped me feel more confident, as I am feeling nervous about A starting school” (first experience of having a child transitioning to school).

## Slide 6: What we did with schools and feedback
The Transition OAG document was shared with both settings when planning transition support. DLP Additional meetings took place with Sencos and paperwork was shared with the schools.
The schools sent staff to observe the children in their nursery settings and then we scheduled additional visits to the new school with the group of children. The groups of children and staff were warmly welcomed at both schools. One school sent staff to story sessions in the nursery’s Acorn Wood where they read stories. The children really enjoyed the session.
One school set up Class Dojo for the new Reception class in June to share information and welcome families
The reception teacher gave the following feedback, “ This was a good use of time to meet a large proportion of my new class in a familiar space and I’m sure it will support their transition for September. This is very important and useful and we need to do it again next year.”

## Slide 7: What we noticed:
Parent/ carers: The impact of this project has been great. The parents were all on board; they talked to their children about school. They were really pleased their children had visited the schools, spent time in their new classroom and started to develop a relationship with their new teacher before September.
Children: They have been observed by staff in their new space and any additional support which needs to be accessed can be put into place ready for them to start. The children are ready for the next stage in their educational journey.
Staff: Feedback from schools was positive and that the new teachers and TAs felt that they were building good relationships with the children early on. Staff working on the project felt this was really useful and will use this model from now on, building on it where possible.
“We just need to get this transition right for our young people.”

## Slide 8: Impact :
Activities listed in the Transition OAG have been tried and tested during this project and these have had really positive feedback from parents, professionals, staff and children. This has confirmed the good practice ideas available.
Parent feedback - “ … has settled really well into Reception and there has been more than enough support.”
Child feedback – “I like school. Made friends.” “I’m happy I came.” One child gave thumbs up.
Staff report that the children are settled and teachers had good information about their needs ensuring support was in place from the start. “It was good to meet them all beforehand,” and “will definitely have similar practice next year as this was helpful.”
Before transition support (May 2025) | After (November 2025)
50% felt ☹ or 😐 about moving to new school. 37% didn’t know which school they were going to. 33% thought they would do activities to get ready for school. | 100% of children felt 😊 for how they feel about their move to their new schools. 100% of children knew the name of their school and teacher, said they had visited the school and met teachers before starting.

## Slide 9: What we learnt/ Next steps:
To continue with enhanced transition packages for children who we feel may need additional support when starting Reception and a new school.
To continue with parent workshops for transition information and expectations regarding transition to school.
To start transition support earlier in the Spring term once children’s needs have been highlighted and when school places are confirmed.
DLP projects have changed this year, but staff involved in the nursery are going to carry on with the transition support and build on this further using the findings from this project.